## Traceability Matrix
Feature | Acceptance Criteria (from proposal) | Jira Ticket | Status | Notes
Authentication & admin approval | JWT auth; admin-only endpoints protected; registration requires approval | ORA-101 | Done
Job & shift management | Job/shift CRUD; earnings auto-calculated from source records | ORA-108 | Done
Live clock-in/out & calendar | Real-time calendar updates via SignalR | ORA-112 | In progress
Visa compliance engine | System blocks shift create/update when 48hr/fortnight limit exceeded | ORA-120 | In progress | Validate in Week 9 demo-flow check
Expense management | Categorisation, budget calculator with allocation tracking | ORA-125 | Done
Savings goals | Targets, allocation %, contribution & progress tracking | ORA-126 | Done
Analytics dashboard | 7-day / 1-month / 12-month views; Excel & PDF export | ORA-131 | In progress | Needs seeded historical data for 1mo/12mo views
Notifications | Visa, balance and savings alerts with read/unread state | ORA-133 | Not started
Aura AI advisor | Responds using live visa, hours, balance and goal data | ORA-140 | In progress
Admin panel | User management, registration review, platform analytics | ORA-145 | Done
Note: Jira ticket IDs above are placeholders (ORA-xxx) — update to match the live board before Week 9 sign-off.