## Group Timesheet
Group Project Timesheet – Group 4 (OraEarn)
PRT_681 ¦ Charles Darwin University ¦ Weekly project group meetings held in class
Team lead |  | Dharma Bahadur Budhathoki
Meetings |  | Held in class each week (face to face)
Repository |  | https://github.com/itsmekrishnaaaaaa/PRT_681_SYDNEY_GROUP-4
Repository activity shows commit dates from the Git history, which record when files were uploaded. Week dates assume Week 4 began on Monday 17 August 2026.
Week | Group | Team lead | Members and roles | Hour | Activity details | Meeting | Repository activity (Git commits)
Week 04 17–23 Aug | Group 4 | Dharma Bahadur Budhathoki | Krishna Sapkota (S395795) – Database Administrator / Tester Dharma Bahadur Budhathoki (S395172) – Developer / Business Analyst Jenish Gurung (S395321) – Business Analyst / Report Writer | Hour 1 | Reviewed progress against the Group Project Implementation plan and confirmed the OraEarn scope, including the visa work-hour limit, shift and break tracking, expenses, budgets, savings goals, and notifications. | In class | • 17 Aug – Dharma: added proposal, solution, and problem statement with technology-stack research; moved timesheet into the repository • 17 Aug – Krishna: added Week 4 database administrator files • 23 Aug – Dharma: added the frontend and installed required packages (Swagger, PostgreSQL, Entity Framework); added Week 5 research and evidence
|  |  |  | Hour 2 | Dharma presented the project proposal, problem statement, and technology-stack research, and the team agreed to build the application with .NET, Entity Framework, Swagger, and PostgreSQL. Krishna would prototype the database in SQL Server first and then move it to PostgreSQL.
|  |  |  | Hour 3 | Krishna presented the preliminary ER diagram with 10 proposed entities, including the keys, relationships, and normalisation approach, and the team reviewed it against the requirements.
|  |  |  | Hour 4 | Agreed the Week 5 tasks: Krishna to build the database tables, Dharma to set up the application structure, and Jenish to document the requirements and begin the report outline.
Week 05 24–30 Aug | Group 4 | Dharma Bahadur Budhathoki | Krishna Sapkota (S395795) – Database Administrator / Tester Dharma Bahadur Budhathoki (S395172) – Developer / Business Analyst Jenish Gurung (S395321) – Business Analyst / Report Writer | Hour 1 | Reviewed the outcomes of Week 4 and confirmed the approved ER diagram as the basis for the database implementation. | In class | • 26 Aug – Jenish: created personal folder and added Week 4 files
|  |  |  | Hour 2 | Krishna demonstrated the tables, primary and foreign keys, and validation constraints implemented in SQL Server, and the team discussed the data types and relationships.
|  |  |  | Hour 3 | Dharma explained how the application would connect to the database, and the team agreed on the sample data needed for users, jobs, shifts, expenses, and savings goals.
|  |  |  | Hour 4 | Jenish updated the requirements document with the confirmed data fields, and the team recorded the issues found in the first implementation for correction the following week.
Week 06 31 Aug–6 Sep | Group 4 | Dharma Bahadur Budhathoki | Krishna Sapkota (S395795) – Database Administrator / Tester Dharma Bahadur Budhathoki (S395172) – Developer / Business Analyst Jenish Gurung (S395321) – Business Analyst / Report Writer | Hour 1 | Reviewed Week 5 progress and the issues recorded in the first database implementation. | In class | • 1 Sep – Dharma: added authentication DTO and User model; started database connection setup • 1–2 Sep – Jenish: added Week 5 files and UML diagram
|  |  |  | Hour 2 | Krishna presented the SQL Server queries for work-hour monitoring, shift and break calculations, expenses, and savings-goal progress, and the team confirmed they met the application needs.
|  |  |  | Hour 3 | Dharma reported progress on the authentication model and the database connection setup, and the team discussed the constraint test results and the access and data-protection needs for financial information.
|  |  |  | Hour 4 | Jenish and Dharma aligned the report sections and application features with the database work, and the team set the tasks for Week 7.
Week 07 7–13 Sep | Group 4 | Dharma Bahadur Budhathoki | Krishna Sapkota (S395795) – Database Administrator / Tester Dharma Bahadur Budhathoki (S395172) – Developer / Business Analyst Jenish Gurung (S395321) – Business Analyst / Report Writer | Hour 1 | Checked that the database remained consistent with the approved requirements and ER design after the Week 6 changes. | In class | • 7 Sep – Krishna: added Week 5 database files and readme • 7 Sep – Jenish: added Week 6 business analysis and report files • 8 Sep – Dharma: added the application (2 commits)
|  |  |  | Hour 2 | Krishna shared the additional SQL test cases and the edge cases found, such as duplicates, missing values, invalid foreign keys, and boundary values, and the team agreed on the corrections.
|  |  |  | Hour 3 | Dharma demonstrated the first working version of the application, and Dharma and Krishna discussed how it would access user, job, shift, expense, budget, and savings-goal data.
|  |  |  | Hour 4 | Jenish and Krishna updated the project documentation with the schema, key queries, testing activities, and identified issues, and the team planned the Week 8 final review.
Week 08 14–20 Sep | Group 4 | Dharma Bahadur Budhathoki | Krishna Sapkota (S395795) – Database Administrator / Tester Dharma Bahadur Budhathoki (S395172) – Developer / Business Analyst Jenish Gurung (S395321) – Business Analyst / Report Writer | Hour 1 | Carried out a final review of the database against the project requirements with all three members. | In class | • 15 Sep – Dharma: updated timesheet • 17 Sep – Jenish: added Week 7 and Week 8 files • 18 Sep – Dharma: centralised frontend colours, made the application responsive, added show-password on login, improved expense and savings-goal screens, added Week 8 timesheet (pull requests #2 and #3 merged)
|  |  |  | Hour 2 | Krishna reported the results of the final testing of the SQL Server database and the refined work-hour, expense, budget, and savings queries, and the team accepted the database design and agreed to move it to PostgreSQL to match the application.
|  |  |  | Hour 3 | Dharma reported the application updates, including a responsive layout, a show-password option on the login page, and improved expense and savings-goal screens, and the team reviewed them.
|  |  |  | Hour 4 | Jenish compiled the supporting evidence for the report, including the ER design, table structure, and testing results, and the team prepared for the Jira planning in Week 9.
Week 09 21–27 Sep | Group 4 | Dharma Bahadur Budhathoki | Krishna Sapkota (S395795) – Database Administrator / Tester Dharma Bahadur Budhathoki (S395172) – Developer / Business Analyst Jenish Gurung (S395321) – Business Analyst / Report Writer | Hour 1 | Reviewed the Week 8 requirements and discussed how Jira Epics, Stories, and Tasks would be used to organise the OraEarn-WebApp work. | In class | • No commits this week
|  |  |  | Hour 2 | Mapped the main OraEarn features into Epics and Stories, with Jenish writing the user stories from the user’s perspective.
|  |  |  | Hour 3 | Krishna identified the tasks for moving the database from SQL Server to PostgreSQL, including table creation, constraints, data validation, and verification.
|  |  |  | Hour 4 | Krishna listed the testing tasks for each story (positive, negative, boundary, and functional), and the team assigned the Jira tasks and agreed how to record progress and defects.
Week 10 28 Sep–4 Oct | Group 4 | Dharma Bahadur Budhathoki | Krishna Sapkota (S395795) – Database Administrator / Tester Dharma Bahadur Budhathoki (S395172) – Developer / Business Analyst Jenish Gurung (S395321) – Business Analyst / Report Writer | Hour 1 | Reviewed the Jira board and the tasks planned for the week. | In class | • 29 Sep – Krishna: uploaded Week 6 files and individual timesheet
|  |  |  | Hour 2 | Krishna presented the schema converted from SQL Server to PostgreSQL, including the constraints and data types, and the team reviewed it against the application’s data model.
|  |  |  | Hour 3 | Discussed the demo data for student-visa and citizen accounts and agreed the test cases for the visa limit, pay calculation, expenses, and savings allocations.
|  |  |  | Hour 4 | Reviewed each member’s uploaded evidence and timesheet in the repository, and Jenish planned the structure of the user manual.
Week 11 5–11 Oct | Group 4 | Dharma Bahadur Budhathoki | Krishna Sapkota (S395795) – Database Administrator / Tester Dharma Bahadur Budhathoki (S395172) – Developer / Business Analyst Jenish Gurung (S395321) – Business Analyst / Report Writer | Hour 1 | Reviewed the test plan and the defects still open in Jira from earlier testing. | In class | • 6 Oct – Krishna: uploaded project files (5 commits)
|  |  |  | Hour 2 | Krishna reported the test results, including the visa-limit boundary cases, and the team prioritised the defects by severity.
|  |  |  | Hour 3 | The team retested the fixes and ran regression checks, and confirmed that the application results matched the database records.
|  |  |  | Hour 4 | Jenish completed the OraEarn User Manual, and the team prepared the final presentation and assigned each member’s section.