## Sheet1
Week | StudentId | Name | Hours [1-6] | Activity details
Week 04 | S395172 | Dharma Bahadur Budhathoki | 1 | Identified OraEarn as the most suitable project concept for helping hourly workers manage earnings, expenses, and savings in one platform.
Week 04 | S395172 | Dharma Bahadur Budhathoki | 1 | Analysed existing alternatives and competitors for shift tracking, budgeting, and Developed the initial project canvas for OraEarn, focusing on target user.
Week 04 | S395172 | Dharma Bahadur Budhathoki | 1 | Defined the core functionality of OraEarn, including job and hourly-rate management, shift tracking, automatic pay calculation, expense tracking, savings goals, and financial analytics.
Week 04 | S395172 | Dharma Bahadur Budhathoki | 0.5 | Discussed student visa work-hour monitoring and designed the concept for alerts to help users manage their permitted working hour
Week 04 | S395172 | Dharma Bahadur Budhathoki | 2 | Finalised the OraEarn project concept with the group (Aura, earnings-to-expenses-to-savings, visa alerts, analytics) so Krishna, Jenish and Suraj shared one product picture.
Week 05 | S395172 | Dharma Bahadur Budhathoki | 1 | Reviewed required OraEarn features and translated them into technical tasks as Developer and Scrum Master so the team had a shared sprint backlog.
Week 05 | S395172 | Dharma Bahadur Budhathoki | 1 | Contributed as Scrum Master by coordinating with team members on GitHub branching, pulling the latest changes from main, resolving merge conflicts correctly, and agreeing on a review process before merging changes.
Week 05 | S395172 | Dharma Bahadur Budhathoki | 1 | Participated in the class ERD discussion as Scrum Master and applied normalisation with Krishna so tester tables match the application models.
Week 05 | S395172 | Dharma Bahadur Budhathoki | 2 | Started the OraEarn application development by setting up the backend and frontend project structure, configuring the development environment, and preparing the application for further implementation.
Week 05 | S395172 | Dharma Bahadur Budhathoki | 1 | Set up the initial database context and required development packages, then configured and edited the database models and attributes according to the final ERD.
Week 06 | S395172 | Dharma Bahadur Budhathoki | 1 | Researched how to connect the OraEarn application to the database, including the required packages, connection configuration, and Entity Framework setup for PostgreSQL.
Week 06 | S395172 | Dharma Bahadur Budhathoki | 1 | Completed the frontend and backend project setup using the required packages and configured the development environment for further implementation.
Week 06 | S395172 | Dharma Bahadur Budhathoki | 2 | Developed frontend and backend according to the final ERD and finalised the database schema so Krishna's tables and Jenish's SRS used the same names.
Week 06 | S395172 | Dharma Bahadur Budhathoki | 1 | Started the Aura AI chat feature with the backend as the main focus; the frontend chat interface still needs to be refined.
Week 06 | S395172 | Dharma Bahadur Budhathoki | 1 | As Scrum Master, attended the individual meeting to review Week 6 database connection, packages, ERD-based setup, Aura backend start, and remaining frontend work.
Week 07 | S395172 | Dharma Bahadur Budhathoki | 1 | Developed application authentication, including registration, login, JWT tokens, and protected access for users and admin.
Week 07 | S395172 | Dharma Bahadur Budhathoki | 1 | Built the admin dashboard so pending registrations can be reviewed, approved, or rejected, and admin-only pages stay restricted.
Week 07 | S395172 | Dharma Bahadur Budhathoki | 2 | Implemented expense CRUD (create, read, update, and delete) using REST APIs in ASP.NET Core, including expense records and related category data.
Week 07 | S395172 | Dharma Bahadur Budhathoki | 1 | Used REST with .NET and Swagger while building these features, to test and document the auth, admin, and expense endpoints.
Week 07 | S395172 | Dharma Bahadur Budhathoki | 1 | As Scrum Master, attended the individual meeting to review Week 7 authentication, admin dashboard and expense CRUD, and to plan Week 8 Swagger and AI chatbot work with the team.
Week 08 | S395172 | Dharma Bahadur Budhathoki | 1 | Completed Swagger documentation and testing for the REST APIs covering auth, admin, jobs, shifts, and expense endpoints.
Week 08 | S395172 | Dharma Bahadur Budhathoki | 2 | Implemented jobs and shift tracking in OraEarn, including the calendar view, hours and pay calculation, and live shift flow.
Week 08 | S395172 | Dharma Bahadur Budhathoki | 1 | Added student visa 48-hour fortnight monitoring on shifts and analytics, and implemented dashboard Excel/PDF export (EARN-147) myself so the data-analyst screens were not empty.
Week 08 | S395172 | Dharma Bahadur Budhathoki | 1 | Started the Aura AI chatbot UI and backend so users can ask about hours, savings, and visa limits.
Week 08 | S395172 | Dharma Bahadur Budhathoki | 1 | As Scrum Master, ran the Week 8 progress review to check Swagger, the running application, remaining Aura work, and each member's next ticket.
Week 09 | S395172 | Dharma Bahadur Budhathoki | 1 | Packed the Assessment 2 Word file with labelled figures, GitHub proof, and Scrum Master diagrams.
Week 09 | S395172 | Dharma Bahadur Budhathoki | 1 | Fixed Swagger register form so swagger.json returns 200, then ran live API tests (token hidden).
Week 09 | S395172 | Dharma Bahadur Budhathoki | 2 | Drew architecture, use-case, add-shift sequence and team ERD workshop pages after the group design talk.
Week 09 | S395172 | Dharma Bahadur Budhathoki | 1 | Ran GET /health in Swagger (200) and Aura /docs tests. No demo passwords in the upload.
Week 09 | S395172 | Dharma Bahadur Budhathoki | 1 | As Scrum Master, assembled the Learnline pack and kept the team on branch app-s395172.
Week 10 | S395172 | Dharma Bahadur Budhathoki | 1 | Updated my timesheet and renamed the Learnline submission files to Dharma Bahadur Budhathoki (S395172).
Week 10 | S395172 | Dharma Bahadur Budhathoki | 2 | Final review of the progress report, figures, and clickable GitHub / Jira links for Week 10 upload.
Week 10 | S395172 | Dharma Bahadur Budhathoki | 1 | As Scrum Master, checked the private-repo invite note and that clone app-s395172 is still on the cover.
Week 10 | S395172 | Dharma Bahadur Budhathoki | 1 | Prepared the Week 10 Learnline zip (report, my timesheet weeks 4-10, meeting logs).
Week 10 | S395172 | Dharma Bahadur Budhathoki | 1 | Polished remaining captions: Swagger tests, UML/ERD diagrams, and individual hours through Week 10.
Total hours (Week 04-10) | S395172 | Dharma Bahadur Budhathoki |  | Must stay within 1-6 hours per week. Week 04=5.5, Weeks 05-10=6 each. Total 41.5.