## Sheet1
Week | StudentId | Name | Hours [1-6] | Activity details
Week 04 | S395172 | Dharma Bahadur Budhathoki | 1 | Identified OraEarn as the most suitable project concept for helping hourly workers manage earnings, expenses, and savings in one platform.
Week 04 | S395172 | Dharma Bahadur Budhathoki | 1 | Analysed existing alternatives and competitors for shift tracking, budgeting, and Developed the initial project canvas for OraEarn, focusing on target user.
Week 04 | S395172 | Dharma Bahadur Budhathoki | 1 | Defined the core functionality of OraEarn, including job and hourly-rate management, shift tracking, automatic pay calculation, expense tracking, savings goals, and financial analytics.
Week 04 | S395172 | Dharma Bahadur Budhathoki | 0.5 | Discussed student visa work-hour monitoring and designed the concept for alerts to help users manage their permitted working hour
Week 04 | S395172 | Dharma Bahadur Budhathoki | 2 | Finalised the OraEarn project concept, including the Aura AI advisor, earnings-to-expenses-to-savings flow, savings goals, analytics dashboard, notifications, and target users.
Week 05 | S395172 | Dharma Bahadur Budhathoki |  |  | 1 | Reviewed the required OraEarn features and translated the final requirements into technical requirements for the application as the main Developer.
Week 05 | S395172 | Dharma Bahadur Budhathoki |  |  | 1 | Contributed as Scrum Master by coordinating with team members on GitHub branching, pulling the latest changes from main, resolving merge conflicts correctly, and agreeing on a review process before merging changes.
Week 05 | S395172 | Dharma Bahadur Budhathoki |  |  | 1 | Participated in the class discussion of the OraEarn ERD and applied database normalisation principles to identify and reduce data redundancy and improve data integrity.
Week 05 | S395172 | Dharma Bahadur Budhathoki |  |  | 2 | Started the OraEarn application development by setting up the backend and frontend project structure, configuring the development environment, and preparing the application for further implementation.
Week 05 | S395172 | Dharma Bahadur Budhathoki |  |  | 1 | Set up the initial database context and required development packages, then configured and edited the database models and attributes according to the final ERD.
Week 06 | S395172 | Dharma Bahadur Budhathoki | 1 | Researched how to connect the OraEarn application to the database, including the required packages, connection configuration, and Entity Framework setup for PostgreSQL.
Week 06 | S395172 | Dharma Bahadur Budhathoki | 1 | Completed the frontend and backend project setup using the required packages and configured the development environment for further implementation.
Week 06 | S395172 | Dharma Bahadur Budhathoki | 2 | Developed the frontend and backend according to the final ERD and finalised the database schema, models, and attributes to match the normalised design.
Week 06 | S395172 | Dharma Bahadur Budhathoki | 1 | Started the Aura AI chat feature with the backend as the main focus; the frontend chat interface still needs to be refined.
Week 06 | S395172 | Dharma Bahadur Budhathoki | 1 | Attended the individual meeting to review Week 6 progress, the database and application setup, and the remaining frontend work.